## ListOfFeatures
Product Backlog - IL Marino(List of your features)
User Stories / List of features
As a site visitor, one can make get a bill for the completed order online to dine in or take away.
The main page has framework for news articles(for example new dishes)
In the reservation page, user can make order order and reserve a table if one intends to sit and eat in the restaurant.
Admin/Employee can add posts, they can modify and remove reservations.
Admins:
can make changes in the comments.
Users:
can post comments on front page posts
can give feedback.
can make online order and pay the bill while picking up the order.

## sprint1
Sprint Backlog : Sprint 1 Feb 7 - Feb 11
BACKLOG TASK & ID | STORY POINTS (NR) | ASSIGNED TO | STATUS
User Story/ Feature #1
Task : Generate a bill for the order |  | Hafiz | Planned
Task : Create a framework for news on main page |  | Anton | Planned
Task: Generate a database for online order, reserve a table. |  | Syed | Planned
Task:
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL
Hints:
During this week, you should update your exisiting pages that is your pages have universarl header and footer.
Upload this excel file to your project Repo in GitHub and update it regulaly.
You have planned your features and have distributed work among your team members
You have designed your database. Make sure that each member has his/her own table to work with.
You have create a GitHub repo and each member is added as collaborator.
Please make regular commits and get familiar with the development activities by utilizing version control.
Uploaing your files to GitHub repo is not acceptable. It will have negative impact on your grade.
Ask questions during the consultation sessions if you are not sure about how you are proceeding

## sprint2
Sprint Backlog : Sprint 2 (Feb 14 - Feb 18)
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS
User Story #1
Making a Confirmation page upon successful reservation by visitor and generating a random unique string as a reservation id, which can be used to modify reservation. |  | Syed | Ongoing
Starts to make a payment receipt to the customer who ordered some food items by making required tables in the database. This can be done by joining relative tables together. |  | Hafiz | Ongoing
User Story #2
Task
Task
Task
Task
r
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL
Hints:
You are working on tasks that you have been assigned to in your team.
You are present in your team meetings.
You are familiary with the GitHub repo for your project work.
You are doing regular commits and you have the latest version of the website in your local device.

## sprint3
Sprint Backlog : Sprint 3 (Feb 21 - Feb 25)
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS
User Story #1
Task : Make a list of categories of products | 2 | Pekka | Ongoing
Task : List products based on categories | 2 | Juha
Task : Search products | 4 | Johanna
Task: Display products | 2 | Markku
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL
Hints:
You are working on tasks that you have been assigned to in your team.
You are present in your team meetings.
You are familiary with the GitHub repo for your project work.
You are doing regular commits and you have the latest version of the website in your local device.
Finalize your work and start to preare for the project review.
Make sure that your repository, shell.hamk.fi servers all have the latest version of your website.